## Hoja1
Project planning
Planificación del proyecto
Grupo de trabajo (Workgroup): | K
horas total en casa (Total hours at home:): | 8
horas total en clase (Total hours in class:): | 20.25
Semana 1 (Week 1) |  | Tiempo total previsto (Total expected time): | 1 |  | Tiempo total previsto (Total expected time): | 6.75
Tareas a realizar en casa (individual, grupo) (Tasks to perform at home (individual, group)) | Persona(s) responsable(s) (Responsible persons) | Tiempo previsto(h) (Total expected time) (Tasks to be done in class (individual, group)) | Tareas a realizar en clase (individual, grupo) Tasks to be done in class (individual, group) | Persona(s) responsable(s) (Responsible persons) | Tiempo previsto(h) (Expected time (h))
Discuss the project | grupo | 1 | Setup device and sensor | Tegshig | 2.25
|  |  | Create connection and do tests to check if right values being received | Luca | 2.25
|  |  | Start design of Node-Red | Tim | 2.25
Entregables (Deliverables)
Upload Microcontroller code
Semana 2 |  | Tiempo total previsto: | 3 |  | Tiempo total previsto: | 6.75
Tareas a realizar en casa (individual, grupo) | Persona(s) responsable(s) | Tiempo previsto(h) | Tareas a realizar en clase (individual, grupo) | Persona(s) responsable(s) | Tiempo previsto(h)
Design Website with dummy values and discuss the project | grupo | 2 | Connect Microcontroller to Node-Red and receive values | Tegshig | 2.25
Discuss the project | grupo | 1 | Setup connection to Node-Red and send values to website | Luca | 2.25
|  |  | Finalize the website | Tim | 2.25
Entregables
Upload Node-Red code
Semana 3 |  | Tiempo total previsto: | 1 |  | Tiempo total previsto: | 6.75
Tareas a realizar en casa (individual, grupo) | Persona(s) responsable(s) | Tiempo previsto(h) | Tareas a realizar en clase (individual, grupo) | Persona(s) responsable(s) | Tiempo previsto(h)
Discuss the project | grupo | 1 | Trouble shooting | Tegshig | 2.25
|  |  | Finalising project | Luca | 2.25
|  |  | Optimizing website | Tim | 2.25
Entregables
Semana 4 |  | Tiempo total previsto: | 3 |  | Tiempo total previsto: | 0
Tareas a realizar en casa (individual, grupo) | Persona(s) responsable(s) | Tiempo previsto(h) | Tareas a realizar en clase (individual, grupo) | Persona(s) responsable(s) | Tiempo previsto(h)
Trouble shooting | grupo | 1
Finalising project | grupo | 1
Discuss the project | grupo | 1
Entregables
Upload Project